## Project Schedule
IAC Internship Progra 2023 - Data Analytics - Project Schedule
|  | PROJECT START DATE | 2023-07-31
|  | Display Week Sr No | 1 | [10 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25
 | time axis 2023-07-31 to 2023-10-01
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2023-07-31 to 2023-10-01
1 | Week 1 | Project Overview |  |  |  |  | 0 | 2023-08-05
1.1 | Week 1 |  | Project Onboarding |  |  |  | 2023-07-31 |  |  |  | Completed
1.2 | Week 1 |  | Attended project onboarding session |  |  |  | 2023-08-01 |  | 2023-08-01 | 1 | Completed
1.3 | Week 1 |  | Problem Statement |  |  |  | 2023-08-05 |  | 2023-08-05 | 2.5 | Completed
1.4 | Week 1 |  | Understanding the Problem statement |  |  |  | 2023-08-06 |  | 2023-08-06 | 2 | Completed
1.5 | Week 1 |  | Identifying the Business Problem |  |  |  | 2023-08-10 |  | 2023-08-10 | 2.5 | Completed
1.6 | Week 1 |  | Data collection for problem statement |  |  |  | 2023-08-11 |  | 2023-08-11 | 2 | Completed
2 | Week 2 | Project Initiation |  |  |  |  | 2023-08-07 | 2023-08-19
2.1 | Week 2 |  | Have a breif at the resources before project initiation |  |  |  | 2023-08-07 |  | 2023-08-07 | 2 | Completed
2.2 | Week 2 |  | Filled Project Charter |  |  |  | 2023-08-08 |  | 2023-08-09 | 1.5 | Completed
2.3 | Week 2 |  | Requirment elicitation questinnaire |  |  |  | 2023-08-09 |  | 2023-08-11 | 3 | Completed
2.4 | Week 2 |  | Weekly meeting attended |  |  |  | 2023-08-10 |  | 2023-08-12 | 2 | Completed
Week 3
2.5 | Week 3 |  | SRS Document |  |  |  | 2023-08-12 |  | 2023-08-13 | 1 | Completed
2.6 | Week 3 |  | Attended requirment elicitation |  |  |  | 2023-08-14 |  | 2023-08-20 | 3.5 | Completed
2.7 | Week 3 |  | Weekly meeting attended |  |  |  | 2023-08-19 |  | 2023-08-19 | 2 | Completed
3 | Week4 | Project Planning |  |  |  |  | 2023-08-21 | 2023-09-02
3.1 | Week 4 |  | Project completion guide |  |  |  | 2023-08-21 |  | 2023-08-22 | 3 | Completed
3.2 | Week 4 |  | Work breakdown structure |  |  |  | 2023-08-22 |  | 2023-08-23 | 3 | Completed
3.3 | Week 4 |  | Identifying risks |  |  |  | 2023-08-24 |  | 2023-08-24 | 2 | Completed
3.4 | Week 4 |  | Making assumptions |  |  |  | 2023-08-25 |  | 2023-08-25 | 2 | Completed
3.5 | Week 4 |  | Weekly meeting attended |  |  |  | 2023-08-26 |  | 2023-08-26 | 2 | Completed
Week 5
3.6 | Week 5 |  | Project scheduling |  |  |  | 2023-08-27 |  | 2023-08-31 | 2 | Completed
3.7 | Week 5 |  | Filled raid logs |  |  |  | 2023-08-31 |  | 2023-08-31 | 3 | Completed
3.8 | Week 5 |  | Understanding lessons learnt log |  |  |  | 2023-09-01 |  | 2023-09-03 | 3 | Completed
3.9 | Week 5 |  | Weekly meeting attended |  |  |  | 2023-09-02 |  | 2023-09-02 | 2 | Completed
4 | Week 6 | Project Execution |  |  |  |  | 2023-09-04 | 2023-09-16
4.1 | Week 6 |  | Finalised Goals |  |  |  | 2023-09-04 |  | 2023-09-04 | 1 | Completed
4.2 | Week 6 |  | Finalised Metrics |  |  |  | 2023-09-05 |  | 2023-09-06 | 3 | Completed
4.3 | Week 6 |  | Finalised expedted deliverables |  |  |  | 2023-09-06 |  | 2023-09-06 | 3 | Completed
4.4 | Week 6 |  | Finalised resources |  |  |  | 2023-09-07 |  | 2023-09-07 | 3 | Completed
4.5 | Week 6 |  | Weekly meeting attended |  |  |  | 2023-09-09 |  | 2023-09-09 | 2 | Completed
Week 7
4.6 | Week 7 |  | Started performing exploratory data analysis | Data preparation |  |  | 2023-09-10 |  | 2023-09-10 | 3 | Completed
4.6.1 | Week 7 |  |  | Data transformation |  |  | 2023-09-12 |  | 2023-09-12 | 4 | Completed | bar: 2023-07-31
4.6.2 | Week 7 |  |  | Data cleaning |  |  | 2023-09-12 |  | 2023-09-12 | 3 | Completed
4.6.3 | Week 7 |  |  | Solving problem statement |  |  | 2023-09-13 |  | 2023-09-16 | 4 | Completed
4.7 | Week 7 |  | Weekly meeting attended |  |  |  | 2023-09-16 |  | 2023-09-16 | 2 | Completed
4.8 | Week 7 |  | Data analysis |  |  |  | 2023-09-18 |  | 2023-09-19 | 4 | Completed
4.9 | Week 7 |  | Data visualization |  |  |  | 2023-09-20 |  | 2023-09-22 | 3 | Completed
5 | Week 8 | Project Closure |  |  |  |  | 2023-09-23 | 2023-09-28
5.1 | Week 8 |  | Weekly meeting attended |  |  |  | 2023-09-23 |  | 2023-09-23 | 2 | Completed
5.2 | Week 8 |  | Preparing Project report |  |  |  | 2023-09-24 |  | 2023-09-24 | 4 | Completed
5.2 | Week 8 |  | Getting ready with all the deliveribles |  |  |  | 2023-09-24 |  | 2023-09-24 | 4 | Completed
5.3 | Week 8 |  | Uploaded project into github |  |  |  | 2023-09-25 |  | 2023-09-25 | 2 | Completed
5.4 | Week 8 |  | Making Demo video |  |  |  | 2023-09-26 |  | 2023-09-27 | 4 | Completed
5.5 | Week 8 |  | Weekly meeting attended |  |  |  | 2023-09-28 |  | 2023-09-28 | 2 | Completed
5.6 | Week 8 |  | Submitted Project File and Completed all tasks |  |  |  | 2023-09-29 |  | 2023-09-29 | 3 | Completed
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you